## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-ID | Introduction to Project | MUST HAVE | No Dependency | Entire Team | 3- Completed
Sprint 2 | Sprint 2 | US-ID | Workflow Creation and Project Goal Definition | MUST HAVE | Lucidchart | Entire Team | 3- Completed
Sprint 3 | Sprint 3 | US-ID | Architectural Diagram Design (System Flow and Module Interaction) | MUST HAVE | Lucidchart | Guravaiah | 3- Completed
Sprint 4 | Sprint 4 | US-ID | Scraping the the data from youtube and google news, clean and normalize datasets | MUST HAVE | Different Scrapers | Guravaiah | 3- Completed
Sprint 5 | Sprint 5 | US-ID | Implement sentiment analysis | MUST HAVE | Python and Langchain | Guravaiah | 3- Completed
Sprint 6 | Sprint 6 | US-ID | run topic extraction, validate accuracy. | MUST HAVE | Python,langchain and groq api | Guravaiah | 3- Completed
Sprint 7 | Sprint 7 | US-ID | Creation and Integration of kowledge base(Rag database) | MUST HAVE | OpenAI Embeddings,Pinecone and Langchain | Guravaiah | 3- Completed
Sprint 8 | Sprint 8 | US-ID | UI Integration and Query Flow Implementation | MUST HAVE | Streamlit, Recommendation Engine | Divya and Rashi | 3- Completed
Sprint 9 | Sprint 9 | US-ID | Final Testing and System Integration Demo Preparation | MUST HAVE | All previous modules | Guravaiah,Divya and Rashi | 3- Completed
Sprint 10 | Sprint 10 | US-ID | System Deployment (Cloud/Local), CI/CD Setup, Performance Optimization | MUST HAVE | Entire system | Guravaiah and Divya | 3- Completed
Sprint 11 | Sprint 11 | US-ID | Full Documentation (Tech Docs, Architecture, API, UI Flow) & User Training | SHOULD HAVE | All previous modules | Entire Team | 3- Completed
Sprint 12 | Sprint 12 | US-ID | Final Project Demo, Presentation & Submission | MUST HAVE | Completed system | Entire Team | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7